## Team Members
Team Member | Contact Phone | Normal Hours | Normal Workdays
Bob Smith | 555-5676 | 8 | Mon - Fri
Sue Jones | 555-2567 | 8 | Mon - Fri
Tim Thomas | 555-2243 | 8 | Mon - Fri

## Roles
Role | Team Member
Project Manager | You
Documentation Developer | You
Data Warehouse Developer | You
ETL developer | You
Cube Developer | You
Report Developer | You
Testers | You
Release Manager | You

## Solution Schedule
BI Solution Projects | Est Hours | Mon | Tue | Wed | Thur | Fri | Mon | Tue | Wed | Thur | Fri
Interview and Identify: | 28 | Mon: ***************************************
Planning and Documenting: | 18 | Thur: **************************
Create the Data Warehouse | 3 | Mon: ****
Extract, Transform, and Load: | 6 | Mon: **********
Create Cubes: | 6 | Mon: ********
Create Reports: | 6 | Mon: ********
Test the Solution: | 21 | Mon: **; Tue: *************************
Approve, Release, and Prepare for next version: | 9 | Thur: *****************

## Estimated Hours
BI Solution Projects | Task | Action Item | Estimated Hours | Actual Hours
Interview and Identify: | Interviews | Talk To Business Owner | 3
|  | Talk to Mangers | 3
|  | Talk to Users | 3
|  | Talk to DBA | 3
| Document Requirements | Create an informal overview | 3
|  | Create a BI solution worksheet | 3
| Locate Data | Review database tables | 3
|  | Review invoice documents | 3
|  | Review sales awards program | 3
| Discuss Feasibility | Decide if the solution will work | 1
28
Planning and Documenting: | Define Team Roles | What role fit this solution? | 1
| Define Team Members | Who will fill each role? | 1
| Define Team Schedule | When will we need them? | 1
| Discuss Feasibility | Decide if the solution will work | 1
| Define IT requirements | Decide which Server will we use for DW, SSIS, SSAS, SSRS | 1
|  | Verify a time slot of Solution automation jobs | 1
| Define Security requirements | Decide which groups will have access to what? | 1
| Define Licensing requirements | Verify that the company has sufficient licensing | 3
| Estimate the cost | Hours * Wages + and additional 10% for unknowns | 1
| Discuss Feasibility | Decide if the solution will work | 1
| Create formal documents | Complete BI solution worksheet | 3
|  | Create a Development Document | 3
18
Create the Data Warehouse | Create the Database | Create the Tables | 2
|  | Define Constraints | 1
3
Extract, Transform, and Load: | Create ETL Code | Create a SQL Script with ETL code | 3
|  | Create a an SSIS package with ETL code | 3
6
Create Cubes: | Create SSAS Database | Create Dimensions | 3
|  | Create Cubes | 3
6
Create Reports: | Create Prototype Reports | Create SSRS Reports | 3
|  | Create Excel Reports | 3
6
Test the Solution: | Requirements | Verify naming | 3
|  | Verify data domains | 3
|  | Verify formula results | 3
|  | Verify presentation formatting | 3
| Performance | Test SSIS ETL performance | 3
|  | Test SSAS Processing performance | 3
|  | Test SSRS Report performance | 3
21
Approve, Release, and Prepare for next version: | Finalize formal documents | Finish development document | 3
|  | Create a formal overview document | 3
|  | Create a lessons learned document | 3
9
|  | TOTAL | 106.7

## Data Warehouse
Fill this column in! |  |  |  | Fill this column in!
Data Warehouse Objects Worksheet
Object Name | Description | Source | Source Type | Destination Type
DWNorthwindLite | Data Warehouse | chec | Database | Database
DWNorthwindLite.dbo.FactOrders | Fact Table | NorthwindLite.dbo.Orders | Table | Table
| Dimension Key Column | NorthwindLite.dbo.Orders.OrderID | int
| Dimension Key Column | NorthwindLite.dbo.Orders.CustomerID | nchar(5)
| Dimension Key Column | NorthwindLite.dbo.Orders.OrderDate | datetime
| Fact Table | NorthwindLite.dbo.OrderDetails | Table | Table
| Dimension Key Column | NorthwindLite.dbo.OrderDetails.OrderID | int
| Dimension Key Column | NorthwindLite.dbo.OrderDetails.ProductID | int
| Measure Column | NorthwindLite.dbo.OrderDetails.UnitPrice | money
| Measure Column | NorthwindLite.dbo.OrderDetails.Quantity | smallint
| Dimension Table | NorthwindLite.dbo.Categories | Table | Table
| Dimension Key Column | Generated | na
| Dimension Column | NorthwindLite.dbo.Categories.CategoryID | int
| Dimension Column | NorthwindLite.dbo.Categories.CategoryName | nvarchar(15)
| Dimension Table | NorthwindLite.dbo.Products | Table | Table
| Dimension Key Column | Generated | na
| Dimension Column | NorthwindLite.dbo.Products.ProductID | int
| Dimension Column | NorthwindLite.dbo.Products.ProductName | nvarchar(40)
| Dimension Column | NorthwindLite.dbo.Products.CategoryID | int
| Dimension Table | NorthwindLite.dbo.Customers | Table | Table
| Dimension Key Column | Generated | na
| Dimension Column | NorthwindLite.dbo.Customers.CustomerID | nchar(5)
| Dimension Column | NorthwindLite.dbo.Customers.CompanyName | nvarchar(40)
| Dimension Column | NorthwindLite.dbo.Customers.ContactName | nvarchar(30)
| Dimension Column | NorthwindLite.dbo.Customers.Address | nvarchar(60)
| Dimension Column | NorthwindLite.dbo.Customers.City | nvarchar(15)
| Dimension Column | NorthwindLite.dbo.Customers.Country | nvarchar(15)
Object Name | Description | Source | Source Type | Destination Type

## ETL Objects
SSIS ETL Objects Worksheet
Object Name | Type | Description | Source | Destination

## Cubes and Dimensions
SSAS Objects Worksheet
Object Name | Description